## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Assigned to | Assigned to
Sprint 1
User Registration | Yes | Yes | High | Complete | Parth Talaviya | Yes
User Login | Yes | Yes | High | Complete | Parth Talaviya | Yes
Homepage | Yes | Yes | High | Complete | Sahil Aaghra | Yes
Sprint 2 |  |  |  | Complete |  | Yes
Admin Dashboard | Yes | Yes | High | Complete | Parth Talaviya | Yes
Bulk Upload | No | Yes | Medium | Complete | Sahil Aaghra | Yes
Report Generation | Yes | Yes | Medium | Complete | Rudra Vaddoriya | Yes
Manage Brands | Yes | Yes | High | Complete | Rudra Vaddoriya | Yes
Sprint 3 |  |  |  | Complete |  | Yes
Car List | Yes | Yes | High | Complete | Sahil Aaghra | Yes
Manage Cars | Yes | Yes | High | Complete | Parth Talaviya | Yes
Payment Handling | Yes | Yes | High | Complete | Parth Talaviya | Yes
Email Handling | Yes | Yes | Medium | Complete | Parth Talaviya/Rudra Vaddoriya | Yes
Sprint 4 |  |  |  | Complete |  | Yes
User Profile Management | Yes | Yes | Medium | Complete | Parth Talaviya | Yes
Booking Confirmation Notifications | Yes | Yes | High | Complete | Parth Talaviya | Yes
Payment Notifications | Yes | Yes | High | Complete | Parth Talaviya | Yes
Sprint 5 |  |  |  | Complete |  | Yes
User Booking History | Yes | Yes | Medium | Complete | Sahil Aaghra | Yes
Filter and Search Cars | Yes | Yes | Medium | Complete | Rudra Vaddoriya | Yes
OTP for Registration | Yes | Yes | High | Complete | Parth Talaviya | Yes
[7 empty] | Task name | Story | Sprint ready | Priority | Status | Story pts | Assigned to sprint | Assigned To
[7 empty] | User Authentication | Yes | Yes | Low | Completed | 8 | Yes | Ritik kalal
[7 empty] | Homepage | Yes | No | Medium | Completed | 16 | Yes | Ritik kalal
[7 empty] | Post Project | No | Yes | High | Completed | 10 | No | Aayush Shah
[7 empty] | Wishlist | Yes | Yes | Low | Completed | 8 | Yes | Ritik Kalal
[7 empty] | Apply Project | Yes | No | High | Completed | 10 | Yes | Aayush Shah
[7 empty] | Bulkupload | No | Yes | Low | Completed | 8 | Yes | Ketan Parmar
[7 empty] | Profile Management | No | No | Medium | Completed | 10 | No | Ritik Kalal
[7 empty] | Admin Dashboard | Yes | Yes | High | Completed | 8 | No | Ketan Parmar
[7 empty] | Admin CRUDS | No | Yes | High | Completed | 10 | Yes | Aayush Shah
[7 empty] | Payment Integration | Yes | Yes | High | Completed | 16 | Yes | Ritik Kalal
[7 empty] | Invoice Generation | Yes | No | Medium | Completed | 10 | No | Ketan Parmar