## Sheet1
AGILE PROJECT PLAN
Project Name | Car Rental System
Project Manager | Dr. Jignesh Doshi
Project Deliverable
Scope Statement
Start Date | 2024-07-01
End Date | 2024-10-25
Overall Progress
Sprint | Task | Responsible | Start Date | End Date | Duration (Days) | Status
1 | User Registration | Parth Talaviya | 2024-07-01 | 2024-07-04 | 3 | Complete
1 | User Login | Parth Talaviya | 2024-07-05 | 2024-07-07 | 2 | Complete
1 | Homepage | Sahil Aaghra | 2024-07-08 | 2024-07-17 | 9 | Complete
1 | User Profile Management | Sahil Aaghra | 2024-07-18 | 2024-07-22 | 4 | Complete
2 | Admin Dashboard | Parth Talaviya | 2024-07-25 | 2024-07-30 | 5 | Complete
2 | Bulk Upload | Sahil Aaghra | 2024-08-01 | 2024-08-07 | 6 | Complete
2 | Report Generation | Rudra Vaddoriya | 2024-08-08 | 2024-08-16 | 8 | Complete
2 | Manage Brands | Rudra Vaddoriya | 2024-08-17 | 2024-08-22 | 5 | Complete
3 | Car List | Sahil Aaghra | 2024-08-24 | 2024-08-31 | 7 | Complete
3 | Manage Cars | Parth Talaviya | 2024-09-01 | 2024-09-06 | 5 | Complete
3 | Payment Handling | Parth Talaviya | 2024-09-07 | 2024-09-12 | 5 | Complete
4 | Email Handling | Parth Talaviya/Rudra Vaddoriya | 2024-09-13 | 2024-09-17 | 4 | Complete
4 | Booking Confirmation Notification | Parth Talaviya | 2024-09-18 | 2024-09-22 | 4 | Complete
4 | Payment Notification | Parth Talaviya | 2024-09-23 | 2024-09-27 | 4 | Complete