## Sheet1
Agile Release Plan
Sprint | Task | Start Date | End Date | Duration (Days) | Status | Release Date | Goal
1 | User Registration | 2024-07-01 | 2024-07-04 | 3 | Released | 2024-07-05 | Enable user registration with email verification
1 | User Login | 2024-07-05 | 2024-07-07 | 2 | Released | 2024-07-08 | Allow registered users to log in
1 | Homepage | 2024-07-08 | 2024-07-17 | 9 | Released | 2024-07-18 | Redirect users to the homepage
1 | User Profile Management | 2024-07-18 | 2024-07-22 | 4 | Released | 2024-07-23 | Enable users to manage their profiles
2 | Admin Dashboard | 2024-07-25 | 2024-07-30 | 5 | Released | 2024-07-31 | Provide admins with a dashboard for management
2 | Bulk Upload | 2024-08-01 | 2024-08-07 | 6 | Released | 2024-08-08 | Allow bulk uploading of car listings
2 | Report Generation | 2024-08-08 | 2024-08-16 | 8 | Released | 2024-08-17 | Generate reports for tracking progress
2 | Manage Brands | 2024-08-17 | 2024-08-22 | 5 | Released | 2024-08-23 | Manage different car brands in the system
3 | Car List | 2024-08-24 | 2024-08-31 | 7 | Released | 2024-09-01 | Display available cars for users to choose from
3 | Manage Cars | 2024-09-01 | 2024-09-06 | 5 | Released | 2024-09-07 | Manage car details and availability
3 | Payment Handling | 2024-09-07 | 2024-09-12 | 5 | Released | 2024-09-13 | Handle payments securely for bookings
4 | Email Handling | 2024-09-13 | 2024-09-17 | 4 | Released | 2024-09-18 | Set up email notifications for users
4 | Booking Confirmation Notification | 2024-09-18 | 2024-09-22 | 4 | Released | 2024-09-23 | Notify users upon successful booking
4 | Payment Notification | 2024-09-23 | 2024-09-27 | 4 | Released | 2024-09-28 | Notify admin and user after successful payment
4 | Invoice Generation | 2024-09-28 | 2024-10-04 | 7 | Released | 2024-10-05 | Generate invoice PDFs for user transactions
5 | Filtering & Searching Products | 2024-10-05 | 2024-10-10 | 5 | Planned | 2024-10-11 | Enable users to filter and search for cars
5 | Upcoming Rentals | 2024-10-11 | 2024-10-15 | 4 | Planned | 2024-10-16 | Show users upcoming rental options

## Sheet2
This section is for the drop-down list
Planned
Ongoing
Released